## Roles
Roles | Name
PO | Lyu Yunfan
SM | Shao Xiaodan
DEV | Sun Yichu, Ma Yuqing, Xiong Yike, Zeng Linghao

## Backlog
Product Backlog: Location Track
Product ID | Product name | Product content (functions) | Priority | Sprint |  | Updated_status
1 | Location Track | To develop an application able to track registered users' location | Must | 1 | Work in Progress | done
Sprint Backlog
Task ID | Task name | Content | Priority |  | Status | Updated_status
1 | Location Track | To develop an application able to track registered users' location | must |  | Work in Progress | done
2 | User registration and login process | Database: account register,login,logout,forget password | must |  | to do
|  | Appliction & User Interface | must |  | to do
3 | Compatible development of basic interfaces on maps | Map API (standard map, ie: Google map, Gaode map) | must |  | to do
4 | Development of gps location | Real time gaps location | must |  | to do
5 | Development of friend radar | Friend radar, search and add the friend nearby | should |  | to do
6 | Development of location sharing | Real-time location sharing with friends | should |  | to do
7 | Development of multi location sharing | Multi sharing applied for team | should |  | to do
8 | Improvement of multi location accuracy | Improvement of dynamic alignment accuracy | could |  | to do
9 | Development of media sharing | Look back previous trajector and share it to social media provided with the application, e.g. friend circle, weibo. Then present users with either a tracking poster or a short tracking video | could |  | to do
10 | Development of special functions | Special functions：users can share location after a mutual agreement. Modes available: parent mode, girlfriend mode, teacher mode | could |  | to do
11 | Development of API interface | Provide specific scene API interface, precise positioning of small scene, such as mall, amusement park, specific tourist attractions | could |  | to do
12 | Development of privacy protection | Privacy protection: delete and update the data periodically | could |  | to do
13 | Development of navigation mode | Navigation mode. Application scenarios: provide AR route guidance between users and estimate the amount of time for finding the other friend | could |  | to do
14 | Testing |  | must
15 | Project Close |  | must

## Sprint Timeline
Sprint Timeline
Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Planning | standup meeting | standup meeting | standup meeting | standup meeting | standup meeting | standup meeting | standup meeting | standup meeting
|  | refinement |  |  |  | refinement |  |  | review
retro
| Duration | Participants
Sprint Planning | Maximum 4 hours for 10 days sprint period | DEV+SM+PO
Sprint Standup Meeting | Maximum 15 minutes, no sitting | Only DEV speak
Sprint Refinement | Maximum 30% of DEV team capacity | DEV+SM
Sprint Review | Maximum 2 hours for 10 days sprint period | DEV+SM+PO
Sprint Retrospect | Maximum 1.5 hours for 10 days sprint period | DEV+SM+PO

## Daily Scrum
DEV | Sprint Timeline
Day | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Sun Yichu | Challenges on developing online map interfaces |  | Difficulties in linking username with locations on live map | [5 empty] | Almost done
Xiong Yike | Managing to finish the API Documentation |  |  | Challenges on hashing user data for privacy protection |  | Trying to complete API for features and functions |  | Fix the problem that the tracking is not stable |  | Hot fixes
Ma Yuqing | Challenges on dynamic alignment accuracy |  | For privacy protection, how frequent should we delete and update the data |  | How the poster of user trajectory should be visually designed |  | How to cope with the situation if multiple users need to share their location simultaneously |  | Alomost done
Zeng Linghao | Friend radar connection |  | Media sharing connection |  |  | Fix the problem of friend privacy |  | Improvement on user experience | Alomost done